 -
 -
## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

PROJECT NUMBER	1
PROJECT NAME	Organisational Information sharing and Leave Management System
PROJECT MENTOR (sponsor)	Shahid Ahmed (Eklavya Foundation)
TEAM MEMBERS	Ananthula Sai Ravichandra
	Krishiv Gupta
	Chaitanya Thogata
	Aditya Chandramouli
	Sai Aditya

## Status
PROJECT NUMBER	1
PROJECT NAME	Organisational Information sharing and Leave Management System
PROJECT MENTOR (sponsor)	Shahid Ahmed (Eklavya Foundation)

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client	Coordination	Ravi	0.5	0.3	Done		0.2	66.6666666666666
GIT Repository setup	Preparation	Chandramouli	0.5	0.2	Done		0.3	150
Client meeting	Coordination	All	1	1	Done	Meeting happened on 25th Jan	0	0
MoM creation	Documentation	Chaitanya	1	1	Done	Resolved some ambiguity on the product structure and clarified requirements	0	0
Project Plan writeup	Documentation	Ravi	1	1	Done		0	0

Week 2 (January 22 - January 28)
Fix meeting with client	Coordination	Aditya	1	1	Done		0	0
MoM creation	Documentation	Chaitanya	1	1.5	Done		-0.5	33.33334
Project Plan writeup	Documentation	Ravi	1	0.5	Done		0.5	100
Client meeting	Coordination	All	0.75	1	Done	Clarified some doubts regarding the requirements and also asked for requirements and hierarchy doc	-0.25	25
Stauts Tracker	Documentation		1	1	Done		0	0
Project Synopsis writeup	Documentation	Ravi	2	1.5	Done		0.5	33.33334
Project Synopsis writeup	Documentation	Krishiv	1.5	1	Done		0.5	50

Week 3 (January 29 - February 4)
Learning Mern		Ravi, Krishiv, Aditya Chandramouli, Chaitanya, Sai Aditya			Done
Team discussion and splitting work		Ravi, Krishiv, Aditya Chandramouli, Chaitanya, Sai Aditya	2	2.5	Done		-0.5	20
Basic Dashboard Design		Ravi, Krishiv, Aditya Chandramouli, Chaitanya, Sai Aditya			Done
Week 4 (February 5 - February 12)
Fix meeting with client	Coordination	Sai Aditya	0.3	0.3	Done		0	0
Team discussion	Coordination	Ravi, Krishiv, Aditya Chandramouli, Chaitanya, Sai Aditya	1.5	2	Done		-0.5	25
MoM creation	Documentation	Chaitanya Thogata, Krishiv	0.75	0.75	Done		0	0
Client Meeting	Coordination	Sai Aditya, Ravi	1	1	Done		0	0
Software Requirements Documentation	Documentation	Aditya Chandramouli, Chaitanya, Krishiv	2.5		Ongoing

Week 6 (February 13 - February 19)
Client Meeting	Coordination	Ravi,Sai Aditya,Krishiv	1	0.66	Done		0.34	51.5151515151515
SRS approval	Coordination	Sai Aditya,Ravi,Krishiv,Chaitanya,Aditya Chandramouli	1	0.5	Done		0.5	100
Database Setup	Development	Ravi, Krishiv	1	2	Done		-1	50
FIGMA design to be shown to the client	Design	Krishiv,Ravi,Aditya	3	2	Done		1	50
Tentative Start of Coding - This Week
Login/Signup page Figma	Design	Sai Aditya	2	1.5	Done		0.5	33.3333333333333

Week 7 (February 20 – February 26)
Login page	Design	Sai Aditya	3	4	Done		-1	25
Database integration with client’s server	Development	Krishiv,Ravi,Aditya	2	3	Done		-1	33.3333333333333
Landing page	Design	Aditya Chandramouli, Chaitanya	3	3	Done		0	0
Team Meeting	Coordination	Sai Aditya,Ravi,Krishiv,Chaitanya,Aditya Chandramouli	3	3	Done		0	0
Week 8 (February 27 – March 5)
LMS page	Design	Chandramouli	3	3	Ongoing		0	0
Team Meeting	Coordination	Sai Aditya,Ravi,Krishiv,Chaitanya,Aditya Chandramouli	3	3	Done		0	0
Events Page	Design	Chaitanya	3	3	Ongoing		0	0
LMS page	Development	Chandramouli	2	3	Ongoing		-1	33.3333333333333
Heirarchy Coding	Design	Ravi,Krishiv	3	4	Ongoing		-1	25
Week 9 (March 6 – March 10)
Landing page	Development	Krishiv	2	3	Done		-1	33.3333333333333
My leaves Page	Development	Ravi,Krishiv	5	6	Done		-1	16.6666666666667
Leave Requests Page	Development	Krishiv	3	4	Done		-1	25
Login page	Development	Sai Aditya	4	5	Done		-1	20
Profile Page	Development	Chaitanya	3	5	Done		-2	40
Events Page	Development	Aditya Chandramouli	4	5	Done		-1	20
Backend Intergration	Development	Ravi	3	5	Done		-2	40
Hierarchy Coding	Development	Ravi, Krishiv	4	6	Ongoing		-2	33.3333333333333
Project Page	Development	Sai Aditya, Chaitanya, Aditya Chandramouli	4	6	Ongoing		-2	33.3333333333333